## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during development and include a detailed description of every step. Explain what problems you encountered, why you made certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log. If external sources where used as reference, please mention them in the description
Subject | Amount of hours | Date | Description | Bonus
project reading | 2 | 2023-11-08 | understand the different points required
including the php skeleton and studying the structure | 2 | 2023-11-08 | I tried to get an idea of how I should set up ,I had some issues to realising that the database and structure had to be implemented directly from phpMyadmin
start of database structure | 1 | 2023-11-08 | structure design and data types
database set with tables in phpMyadmin | 1 | 2023-11-09
set route for controller facility and trying to retrive data | 5 | 2023-11-09 | initially i had no implemented the classes for the tables so i had a bit of issues with this,i thought i didn't need it as i didn't have to use the data,then i realised i needed it to show related data in the response.
creation of classes and implementation of the read function | 3 | 2023-11-10 | the code is very long I have created functions in another file, although I should certainly implement them in the classes but I am confused about the structure
create update and delete functions | 5 | 2023-11-10 | some problems with tags, initially I had set up that I receive an array of id and not values
code review and addition of status code | 2 | 2023-11-10 | I realise that I do not understand clearly the difference between throwing an exception or replying with a status code
research on how to implement cursor pagination and implementation of this | 2 | 2023-11-12 | I watched a tutorial on youtube and then tried to implement it
research to see how to implement validation without laravel | 1 | 2023-11-12
add table employees and some data and classs employee | 1 | 2023-11-13
adding some data to the database and database dump |  | 2023-11-13
export json file from postman |  | 2023-11-13
Total amount of hours | 25